## In words
Building Block | Deliverable | Assigned to | Status | Files involved
1A1 | Location Service (Check 1A1) * Never/Manually * When using the app * Always | Joe | Initial | Covid_App.html app.js
1A2 | Notifications (Toggle 1A2) * On/Off (On > Register) | Joe | Initial | Covid_App.html app.js
1A3 | Time of Overlap (Slider 1A3): * Hours between Infected Visit and Personal visit log | Joe | Initial | Covid_App.html app.js
1B1 | Define COMPANY_ID's (dropdown list 1B1) * Register & obtain * Precreated in Database | Aukje | Initial | COVID_db get_companies.sql app.py (FLASK)
1B2 | Delete options (check 1D1) * Variable in days OR * Auto after 4 weeks OR * Don't delete | Leo | Initial | visit_ids.csv delete.js (new)
2A1 | Create log entry initiated by (2A1): * User > Manually * Phone > Automatically (Location service ON) * Store Initiated > WIFI / Popup > Accept/Decline | Leo | Initial | visit_ids.csv create.js (new)
2B1 | VISIT_ID Composition (2B1) * COMPANY_ID (8 CHAR) * DATE TIME stamp (14 CHAR) * UNIQUE ID (12 CHAR) | Aukje | Active | get_visit_id.py
2C1 | view log screen (2C1) * Companies and Datetime visited * Current Risk Flag * Requires 'refresh' and connect to database | Joe | Initial | visit_ids.csv app.js Covid_App.html
3A1 | Process on User side (3A1) * User tests positive * User receives DOCTOR_KEY * User sends ALERT to database |  | Initial
3B1 | Process on Database side (3B1) * Program creates entries in INFECTED_COMPANIES table for all VISIT_ID's user has sent to database |  | Initial
3C1 | Process on App side (3C1) * If Push notifactions are on User receives warning in case of 'OVERLAP' * If Push notifications are NOT on, app will connect regularly to check for 'OVERLAP' |  | Initial
4A1 | Improve Risk Calculator (4A1) * Find better Dataset * Create more features * Create & Save new models * Integrate into Application |  | Initial
5A1 | Improve Charts (5A1) * Add chart by ZIP code |  | Initial
6A1 | Improve Predictions (6A1) * Find better Prediction Model * Apply to Predictions Page * Automate Launch * Let user set days out and run |  | Initial
7A1 | Create a new page (7A1) * Use User's location * Locate infected Companies through Infected_Companies table in app |  | Initial

## Graphical
COMPONENTS (TABS) OF THE COVID CORNER APPLICATION |  |  |  |  | EXISTING COMPONENTS THAT NEED IMPROVEMENT |  |  |  | OTHER NEW COMPONENTS
| NEW PAGE 7 |  | NEW PAGE 1 |  |  | EXISITING PAGE 2 | EXISITING PAGE 3 | EXISITING PAGE 4 |  | NEW PAGE 5
| 1. SYSTEM SETTINGS | 2. LOGGING AN ENTRY |  | 3. INFECTION ALERT |  | 4. RISK CALCULATOR | 5. CHARTS | 6. PREDICTIONS |  | 7. COVID NEAR ME
2A Log VISIT_ID on phone only
Create log entry initiated by (2A1): * User > Manually
* Phone > Automatically (Location service ON)
* Store Initiated > WIFI / Popup > Accept/Decline
2B VISIT_ID Composition (2B1)
* COMPANY_ID (8 CHAR)
* DATE TIME stamp (14 CHAR)
* UNIQUE ID (12 CHAR)
2C view log screen (2C1)
* Companies and Datetime visited
* Current Risk Flag
* Requires 'refresh' and connect to database
1A: User Settings:
Location Service (Check 1A1)
* Never/Manually
* When using the app
* Alway
Notifications (Toggle 1A2)
* On/Off (On > Register)
Time of Overlap (Slider 1A3):
* Hours between Infected Visit and Personal visit log
1B: Company Settings:
Define COMPANY_ID's (dropdown list 1B1)
* Register & obtain
* Precreated in Database
1C: Doctor Settings:
Process (1C1) * Register
* Obtain Unique Key
* Key needed for user to set 'INFECTED_FLAG
3A Process on User side (3A1)
* User tests positive
* User receives DOCTOR_KEY
* User sends ALERT to database
3B Process on Database side (3B1)
* Program creates entries in INFECTED_COMPANIES table for all VISIT_ID's user has sent to database
3C Process on App side (3C1)
* If Push notifactions are on User receives warning in case of 'OVERLAP'
* If Push notifications are NOT on, app will connect regularly to check for 'OVERLAP'
1D: Visit Log Cleanup
Delete options (check 1D1)
* Variable in days OR
* Auto after 4 weeks OR
* Don't delete
4A Improve Risk Calculator (4A1)
* Find better Dataset
* Create more features
* Create & Save new models
* Integrate into Application
5A Improve Charts (5A1)
* Add chart by ZIP code
6A Improve Predictions (6A1)
* Find better Prediction Model
* Apply to Predictions Page
* Automate Launch
* Let user set days out and run
7A Create a new page (7A1)
* Use User's location
* Locate infected Companies through Infected_Companies table in app

## Lists
Assigned To | Status
Leo | Initial
Joe | Active
Aukje | Completed